## Timeline Template
JOYN FSM - Sample Timeline without Integrations |  | Day
# | Milestone | 1 | 7 | 14 | 21 | 28 | 35 | 42 | 49 | 56 | 63
1 | Setup environments | bar: Day 1
2 | Load Master Data and Metadata | bar: Day 7 to Day 14
3 | Design/Build/Configure 5 use cases (task types) | bar: Day 21 to Day 28
4 | First UAT and feedback for minor setup modifications | bar: Day 35 to Day 42
5 | Second UAT for final confirmation | bar: Day 49
6 | Training | bar: Day 56
7 | Go Live | bar: Day 63
JOYN FSM - Sample Timeline with Integrations |  | Day 1: Day
NOTE: Integration timelines are estimates and may change subject to customer’s SME knowledge for internal systems.
# | Milestone | 1 | 7 | 14 | 21 | 28 | 35 | 42 | 49 | 56 | 63 | 70 | 77
1 | Setup environments | bar: 1
2 | Load/Integrate Master Data and Metadata | bar: 7 to 14
3 | Design/Build/Configure 5 use cases (task types) | bar: 21 to 28
4 | Integrate Transaction Data to/from EAM/ERP system | bar: 35 to 42
5 | First UAT and feedback for minor setup modifications | bar: 49 to 56
6 | Second UAT for final confirmation | bar: 63
7 | Training | bar: 70
8 | Go Live | bar: 77